## Strategy
Pinterest Distribution Strategy - travelsamericas.com
Item | Detail | Why / Note
THE FUNNEL
Funnel | Pin (search result) -> Saved/Clicked -> Landing page (guide) -> Email capture (PDF lead magnet) -> Drip sequence -> Affiliate booking (hotel / insurance / eSIM) | Every pin links to a page with an email capture. Email subs are the primary KPI, clicks are secondary.
Why Pinterest | Search-driven (no follower base needed to start), ~70% female user base, solo female travel is a top vertical, pins surface for 6-12 months vs hours on other platforms | Direct match with your only proven niche: NYC solo/female-solo safety (90% of your Google impressions)
Positioning | "The solo female traveler's safety-first guide to US cities" - NOT "discover iconic cities" | Pinterest profile bio, board names, and every pin reinforce this single positioning
NORTH-STAR TARGETS (12 weeks)
Pins live | 100-120 published pins | Volume is the #1 predictor of early Pinterest traction
Monthly impressions | 25,000-60,000 by week 12 | Wide range - new accounts vary heavily. Below 10k at week 12 = review keywords/format
Outbound clicks | 250-500/month by week 12 | ~0.8-1.2% of impressions is a realistic outbound rate
Email subscribers | 60-150 total by week 12 | Assumes 8-15% landing-page opt-in rate with the PDF magnet
OPERATING MODEL (automation-first, per your choice)
Your weekly time | ~2 hrs: review scheduled queue, approve designs, check scorecard | Production is delegated to templates + scheduler + freelancer
Designer (Fiverr/Upwork) | $60-150 one-time for 6 master templates, then ~$30-60/month for batch fills | Brief is on the "Pin Formats + AI Prompts" sheet
Scheduler | Pinterest native scheduler (free, 30 days ahead) or Tailwind ($25/mo) if you want interval re-pinning + analytics | Start native, upgrade only if volume sustains
AI imagery rule | AI for ILLUSTRATED/flat-design pins (checklists, maps, infographics) only. Use licensed stock photos for photorealistic pins. | Pinterest labels AI-generated images and users distrust fake travel photos. Illustrated style avoids both problems.
HARD PREREQUISITES (block everything else)
1. Ship the NYC itinerary PDF | Your lead magnet URL is still blank in .env. Without it the funnel has no bottom. | Week 1, non-negotiable
2. Join high-CPA programs | SafetyWing / World Nomads (insurance), Airalo (eSIM) - safety audience converts on these, not flights | Week 1
3. Fix homepage thumbnails | LA/Vegas/Orlando cards use images named from another project (Robobionics, Takachar, Navalboats) | Pinterest visitors who click through must not see mismatched images

## Messaging
Messaging Framework
Element | Content | Rationale | Where it points
PILLAR 1: SAFETY CONFIDENCE (50% of pins)
Core message | "You can do this safely - here is exactly how" | Practical, calm, zero fear-mongering. Confidence is the product, safety info is the vehicle. | Checklist, neighborhood breakdown, decision-tree pins
Example titles | "Is NYC Safe for Solo Female Travelers? A Block-by-Block Answer" / "NYC Subway at Night: 5 Rules I Follow Every Time" / "The NYC Safety Checklist I Send Every First-Timer" | First-person voice outperforms institutional voice on Pinterest | Link: nyc-safety-guide, subway-safety-guide, female-solo-guide
PILLAR 2: SOLO INDEPENDENCE (25% of pins)
Core message | "You do not need a travel buddy to see New York" | Emotional hook - permission + empowerment. Highest save-rate pillar. | Itinerary and "solo-friendly spots" pins
Example titles | "Solo Trip to NYC: The 3-Day Itinerary That Actually Works Alone" / "13 Things to Do Alone in NYC (That Don't Feel Lonely)" / "Eating Alone in NYC Without the Awkwardness" | "Alone without lonely" framing tests well in this vertical | Link: solo-trip-to-nyc, solo-itinerary, food
PILLAR 3: INSIDER SPECIFICITY (15% of pins)
Core message | "Block-by-block detail no generic top-10 list gives you" | Differentiates vs big-publisher pins; drives saves as reference material | Map pins, neighborhood comparison pins
Example titles | "Where to Stay in NYC: Safe Neighborhoods Ranked by a Local" / "NYC Neighborhoods After Dark: Where I Walk vs Where I Ride" | Comparison/ranking formats earn the highest outbound CTR | Link: best-areas-to-stay, neighborhood-guide
PILLAR 4: PLANNING & PREP (10% of pins)
Core message | "Arrive prepared, not anxious" | Direct feeder to the PDF lead magnet | Packing list, pre-trip setup, app list pins
Example titles | "Pre-Trip Safety Setup: 7 Things to Do Before You Land in NYC" / "Free 3-Day NYC Solo Itinerary (Printable PDF)" | PDF pins link straight to the email capture | Link: signup/landing page
DESCRIPTION FORMULA (every pin)
Structure | [Hook restating the promise] + [2-3 sentence preview with keywords woven naturally] + [CTA] + 3-5 keyword phrases | Pinterest reads descriptions for search ranking. 100-300 chars ideal. | -
Keywords to weave in | solo travel nyc, solo female travel, nyc safety tips, nyc itinerary, where to stay in nyc, first time nyc, girls trip nyc, new york travel guide | Use 3-5 per pin, never all - keyword stuffing suppresses distribution | -
CTA bank | "Get the free printable itinerary" / "Save this for your trip" / "Full block-by-block guide on the site" / "Grab the safety checklist PDF" | "Save this" CTAs lift save-rate ~15-20% (saves boost future distribution) | -
VOICE RULES
Do | First person, specific numbers ("5 rules", "4 days", "7 neighborhoods"), calm authority, US spelling | Specificity = credibility = saves | -
Do not | Fear-bait ("DANGEROUS areas to AVOID!!"), clickbait gaps ("you won't believe #3"), generic wanderlust ("explore the magic of NYC") | Fear-bait attracts the wrong audience and Pinterest suppresses it; generic = invisible | -

## Target Audience
Target Audience & Personas
Item | Detail | Effort share | What she searches on Pinterest | What to show her
P1 - PRIMARY: The Anxious First-Time Solo Traveler
Who | Woman 24-38, US-based, planning her first solo trip; researches heavily, over-prepares, screenshots everything | ~60% of effort | "solo trip to nyc", "is nyc safe for a woman", "nyc solo itinerary", "things to do alone in nyc" | Safety checklists, itineraries, "you can do this" empowerment pins
Pain point | Wants the trip but fear of being unsafe/alone is the blocker. Friends/family amplify the fear. | - | - | Confidence framing - your entire safety content maps to her
Conversion path | Saves 5-10 pins while dreaming -> clicks itinerary pin when trip becomes real -> downloads PDF -> drip converts to hotel/insurance booking | - | - | She is the email list
P2 - SECONDARY: International First-US-Trip Planner
Who | Woman 25-45 from UK/AU/CA/DE planning first US trip; NYC is the anchor city; longer lead time (3-6 months) | ~25% of effort | "new york first time guide", "nyc tips for tourists", "new york travel guide", "usa trip planning" | Subway/transit explainers, scam-avoidance, neighborhood guides
Why she matters | Your GSC already shows Japan/Vietnam/UK/Mexico impressions; international visitors book MORE (insurance, eSIM, transfers = your highest-CPA offers) | - | - | eSIM + insurance pins target her explicitly
P3 - TERTIARY: The Girls-Trip Organizer
Who | Woman 25-40 planning a group trip; one organizer researches for 4-6 travelers | ~15% of effort | "girls trip nyc", "nyc bachelorette", "group itinerary new york" | Group itinerary and dining pins (you already have group-travel pages)
Why she matters | One click = multiple bookings. Highest revenue-per-visitor persona. | - | - | Do not build new content for her yet - pin existing group pages only
EXPLICITLY NOT TARGETING
Who to ignore | Budget backpackers (no booking budget), luxury travelers (wrong brand), male solo travelers (different search behavior), locals | Zero effort | - | Niche discipline is the whole strategy - generic = invisible

## Site Updates
Website Updates (Text / Imagery / Tracking)
# | Update | Why | How | When | Status (Jun 10)
BLOCKERS - DO BEFORE FIRST PIN
1 | Ship the NYC itinerary PDF lead magnet | NYC_ITINERARY_PDF_URL is blank - the welcome email sends a placeholder. The entire pin->email funnel dead-ends without it. | Export your existing solo-itinerary page content into a designed 8-12 page PDF | Week 1 | NOT STARTED — top blocker
2 | Add email capture above the fold on top 5 landing pages | Pages pins link to (safety guide, solo trip, female solo, best areas, itinerary) must capture emails on first screen, not just footer | Inline form: "Get the free 3-day solo NYC itinerary (PDF)" + first-name/email | Week 1-2 | Not started
3 | Fix homepage thumbnails | LA/Vegas/Orlando cards use wrong-project images (RobobionicsWebThumbnail, NavalboatsStory, TakacharStory filenames) | Replace with licensed city photos | Week 1 | Not started
IMAGERY - PINTEREST REQUIREMENTS
4 | Add one 1000x1500px (2:3) vertical "pinnable" image to every top page | Pinterest needs vertical images; your pages currently only have horizontal banners and 1200x630 OG images. When users hit Save on your site, a vertical asset must exist. | Use your pin templates - same design system. Add descriptive alt text (Pinterest reads it for ranking) | Week 2-3 | Partially mitigated: 10 OG share cards built (in code, NOT deployed). Vertical 1000x1500 pin images still needed
5 | Add Pinterest Save button to article images | One-line script; turns every site visitor into a potential distributor | data-pin-description preset with keyword-rich text | Week 2 | Not started
6 | Validate Rich Pins | Your og:type=article metadata is already in place - run the Rich Pin validator so pins auto-pull title/description | developers.pinterest.com validator, one-time | Week 1 | DONE — claim verified; validator retired, Rich Pins auto-apply
TEXT - LANDING PAGE ALIGNMENT
7 | Match landing H1 to pin promise | If pin says "Block-by-Block Safety Breakdown", the page user lands on must visibly deliver that within one scroll - bounce kills Pinterest distribution | Audit top 5 pages against the pin titles on Messaging sheet | Week 3 | Not started
8 | Add "pin-magnet" mid-article CTAs | "Save this guide to Pinterest for your trip" near the checklist sections | Text + save button | Week 3 | Not started
9 | Update profile-facing pages | About page needs a named author/founder with photo - Pinterest users check profiles before following; anonymity suppresses trust | Short founder bio: why you built a safety-first guide | Week 2 | Not started
TRACKING
10 | UTM scheme on every pin URL | utm_source=pinterest&utm_medium=organic&utm_campaign=[pillar]&utm_content=[pin-id] | Without this you cannot attribute email subs to pins in GA4 | Week 1 | Not started
11 | GA4 conversion event for email signup | Mark signup as key event; build Pinterest channel report | Closes the loop: pin -> visit -> sub | Week 2 | Not started
12 | Pinterest tag (base + signup event) | Even for organic, the tag feeds Pinterest audience insights; required if you ever test ads | Add to layout.tsx alongside gtag | Week 4 | Not started

## 12-Week Plan
12-Week Execution Plan
Cadence after setup: your involvement ~2 hrs/week (copy approval + scorecard). Designer fills templates. Scheduler posts daily. Volume target: 10-15 pins/week from week 3.
Wk | Theme | Deliverables | Owner / hours | Done = | Quality bar / notes | Status (as of Jun 10, 2026)
PHASE 1: FOUNDATION (Weeks 1-2)
1 | Account + funnel foundation | Create Pinterest Business account; claim travelsamericas.com; validate Rich Pins. Ship NYC PDF lead magnet + wire welcome email. Apply: SafetyWing, Airalo affiliate programs. Set UTM scheme. Fix homepage thumbnails. | You (one-time setup ~4 hrs this week only) | Account live, domain claimed, PDF downloadable end-to-end | Test: pin URL -> page -> signup -> email lands with working PDF link | PARTIAL. Done: business account, domain claimed+verified, Rich Pin metadata (og:type=article on ~50 pages, OG blocks on 7 NYC pages, title bugfix, 10 OG cards w/ logo+Bold font). NOT DONE: deploy of OG work, PDF lead magnet, SafetyWing/Airalo applications, homepage thumbnail fix, UTM scheme. Carry-overs move to Week 2.
2 | Boards + design system | Create 8 boards (see Pin Formats sheet for names/keywords). Hire Fiverr designer with the brief OR build 6 Canva master templates yourself. Generate AI background batch (10 illustrated images). Add email capture to top 5 pages. | You 2 hrs + AI agent (designer line item removed) | 8 keyword-named boards; 6 approved master templates | Templates must pass the squint test: title readable at thumbnail size on mobile | STARTS MON JUN 15. Revised: AI agent replaces Fiverr designer for all graphics (decision Jun 10). Must-do this week: DEPLOY pending OG/article changes; ship PDF; apply to affiliate programs; create 8 boards (copy ready); finish profile (avatar+bio+email confirm); 6 pin master templates via agent WITH visual QA gate.
PHASE 2: PRODUCTION RAMP (Weeks 3-5)
3 | First batch - 12 pins | Produce 12 pins from existing NYC pages (4 safety, 3 solo-itinerary, 3 where-to-stay, 2 PDF lead-magnet pins). Write titles/descriptions from Messaging sheet. Schedule 2/day via native scheduler. Add Save buttons + vertical images to top 5 pages. | Designer fills templates; you write copy 1.5 hrs + approve | 12 pins scheduled; save buttons live | Each pin: unique title, 3-5 keywords in description, UTM link | Pending
4 | Batch 2 - 12 pins + baseline | 12 new pins (rotate pillars per Messaging mix). Record baseline in Scorecard. GA4 signup event live. | Designer + you 2 hrs | 24 pins live; Scorecard week-4 row filled | Impressions will be low (<2k) - normal, do not react | Pending
5 | Batch 3 - 15 pins, multi-format | 15 pins: introduce 2 new formats (map pin, stat/myth pin). Re-pin top performers to second relevant board (48h apart). | Designer + you 2 hrs | 39 pins live; all 6 formats tested | - | Pending
PHASE 3: RHYTHM + FIRST CUTS (Weeks 6-8)
6 | Review gate #1 | Scorecard review: rank all pins by saves + outbound clicks. KILL the worst format. Double production on best 2 formats. 12 pins. | You 2.5 hrs | Format decision documented in Scorecard notes | Kill criteria: bottom format by saves/impression after 3+ weeks live | Pending
7 | Batch + group boards | 12 pins. Apply to 3-5 active group boards / Tailwind communities in solo female travel niche. Engagement: follow/save 10 adjacent creators' pins weekly (feeds the algorithm your niche). | You 2 hrs + designer | 51+ pins; 2+ group board acceptances | Group boards must show recent activity - dead boards hurt | Pending
8 | Batch + seasonal start | 12 pins incl. 3 seasonal ("NYC in Fall solo", "Holiday NYC safety") - Pinterest search shifts seasonal 45-60 days ahead. First idea-pin/video test (15-sec checklist animation from template). | Designer + you 2 hrs | 75 pins; 1 video pin live | - | Pending
PHASE 4: OPTIMIZE + DECIDE (Weeks 9-12)
9 | Double down | 15 pins: re-skin top 10 performers with new titles/imagery (same URL is fine if pin image differs). 3 more video pins if week-8 test got distribution. | Designer + you 2 hrs | 90 pins | Re-skinning winners outperforms new guesses ~2:1 | Pending
10 | Landing optimization | 12 pins. A/B the email capture: test "PDF itinerary" vs "safety checklist" magnet on top landing page. Check GA4: pin -> sub conversion by pillar. | You 3 hrs | Opt-in rate benchmark documented (target 8%+) | If opt-in <5%, the magnet or form placement is the problem - not Pinterest | Pending
11 | Batch + outreach prep | 12 pins. Export list of group boards/communities that accepted you -> these are also partnership leads for the B2B track. | You 2 hrs | 114 pins | - | Pending
12 | Review gate #2 - go/no-go | Full funnel review vs targets (Strategy sheet): impressions, clicks, subs. Decide: scale (add designer hours), hold (maintain 10/wk), or fix (diagnose weakest funnel stage). Write next-12-week plan. | You 3 hrs | Decision documented + next-quarter plan | GO = 25k+ monthly impressions OR 50+ subs. NO-GO = <10k impressions AND <20 subs -> diagnose before more volume | Pending

## Pin Formats + AI Prompts
Pin Formats, Boards & AI Image Prompts
Element | Specification | Why | Imagery source / AI prompt
BOARD ARCHITECTURE (create week 2)
Boards | 1) NYC Solo Female Travel 2) NYC Safety Tips 3) NYC Itineraries 4) Where to Stay in NYC 5) NYC Subway + Getting Around 6) Solo Travel Tips for Women 7) NYC Food for Solo Travelers 8) Girls Trip NYC | Board names ARE keywords - never cute names ("Big Apple Dreams" = invisible) | Each board: 200-char keyword description + branded cover
FORMAT 1: CHECKLIST PIN (workhorse - 30%)
Spec | 1000x1500. Bold title top 1/3, 5-7 checklist items with checkmarks, brand bar + URL bottom. Illustrated background, 60%+ white/light space. | Highest save-rate format in travel-safety niche | AI PROMPT: "Flat design illustration, minimalist NYC skyline silhouette at dusk, soft coral and navy palette, large empty space in upper two-thirds for text overlay, vector style, clean, no people, no text" (Ideogram/Canva AI; add text in Canva, never via AI)
FORMAT 2: NEIGHBORHOOD MAP PIN (15%)
Spec | 1000x1500. Stylized illustrated Manhattan/Brooklyn map, 4-6 labeled zones color-coded by "relaxed / aware / ride-dont-walk", legend bottom. | Maps are save magnets - reference material users return to | AI PROMPT: "Stylized illustrated tourist map of Manhattan, flat vector style, soft pastel color zones, landmarks as simple icons, clean white background, no text labels" (add labels in Canva for accuracy - AI text is unreliable)
FORMAT 3: LISTICLE PIN (25%)
Spec | 1000x1500. Number-led title ("7 NYC Neighborhoods Safe at Night"), numbered list teaser showing 3 of 7 items + "see all ->", drives click-through. | Showing partial list = click motivation without clickbait | Background: licensed stock photo (Unsplash/Pexels commercial-ok) with 65% dark overlay. NOT AI - photoreal AI cityscapes get flagged + distrusted
FORMAT 4: ITINERARY/DAY-PLANNER PIN (15%)
Spec | 1000x1500. "3 Days in NYC Solo" - vertical timeline Day 1-3 with one line each, PDF CTA at bottom. | Direct feeder to email capture | Mix: illustrated AI background (Format 1 prompt, daytime palette) + Canva timeline elements
FORMAT 5: STAT/MYTH PIN (10%)
Spec | 1000x1500. Big claim top ("NYC is safer than 90% of large US cities"), 2-line context, source line, brand bar. | Shareable, builds authority, feeds AI-assistant citations too | Solid brand-color background + typography only. No imagery needed - fastest to produce
FORMAT 6: VIDEO/IDEA PIN (5% - test wk 8)
Spec | 9:16, 10-20 sec. Animated checklist reveal or 5-tip countdown with text motion, no voiceover needed, trending audio optional. | Pinterest pushes video distribution; cheap test via Canva animate | Reuse Format 1 design, animate elements in Canva. One per week max until data proves it
PRODUCTION RULES
Text overlay | Max 12 words on image. Title font 60-80pt equivalent - readable at 236px thumbnail. Brand: same 2 fonts + 3 colors every pin. | Consistency = brand recognition in feed | -
AI imagery guardrails | Illustrated/flat/vector styles ONLY. Never photoreal AI of NYC (users spot it, Pinterest labels it, trust dies). Never AI-generated text inside images. | Your niche sells TRUST - one fake-looking image undermines the safety brand | -
Freelancer brief | Hand designer: this sheet + Messaging sheet + brand colors/fonts + 6 master templates request. Batch order: 12-15 fills/week, $2-5/pin typical. | - | -

## Scorecard
Weekly Scorecard - fill every Monday from Pinterest Analytics + GA4
Yellow cells = your weekly inputs. CTR/cumulative columns calculate automatically.
Week | Pins published | Cumulative pins | Impressions | Saves | Outbound clicks | Outbound CTR | Email subs (GA4: pinterest source) | Cumulative subs | Save rate | Notes / decisions
Week 1 |  | 0 |  |  |  | - |  | 0 | -
Week 2 |  | 0 |  |  |  | - |  | 0 | -
Week 3 |  | 0 |  |  |  | - |  | 0 | -
Week 4 |  | 0 |  |  |  | - |  | 0 | -
Week 5 |  | 0 |  |  |  | - |  | 0 | -
Week 6 |  | 0 |  |  |  | - |  | 0 | -
Week 7 |  | 0 |  |  |  | - |  | 0 | -
Week 8 |  | 0 |  |  |  | - |  | 0 | -
Week 9 |  | 0 |  |  |  | - |  | 0 | -
Week 10 |  | 0 |  |  |  | - |  | 0 | -
Week 11 |  | 0 |  |  |  | - |  | 0 | -
Week 12 |  | 0 |  |  |  | - |  | 0 | -
TOTAL | 0 |  | 0 | 0 | 0 | - | 0
Benchmarks / decision rules
Outbound CTR healthy | 0.8% - 1.5% (below 0.5% = weak titles or wrong keywords)
Save rate healthy | 0.5% - 1.0% of impressions (saves predict future distribution)
Week 6 gate | Kill weakest pin format; double best 2
Week 12 GO | 25k+ monthly impressions OR 50+ total subs
Week 12 NO-GO | <10k impressions AND <20 subs -> diagnose funnel stage before adding volume
UTM RULE — apply to every pin link, from pin #1
Format | https://www.travelsamericas.com/<page-path>?utm_source=pinterest&utm_medium=organic&utm_campaign=<pillar>&utm_content=<pin-id>
utm_source | Always exactly: pinterest (lowercase)
utm_medium | Always exactly: organic (switch to paid only if ads are ever tested)
utm_campaign | The messaging pillar, one of: safety / solo / insider / planning
utm_content | Unique pin ID: <format>-<number>, e.g. checklist-01, map-03, listicle-12. Log the ID in your pin tracking so GA4 rows map back to a specific pin
Example | https://www.travelsamericas.com/destination/nyc/solo-itinerary?utm_source=pinterest&utm_medium=organic&utm_campaign=planning&utm_content=itinerary-02
Where to read results | GA4 -> Reports -> Acquisition -> Traffic acquisition, filter session source = pinterest; add secondary dimension session campaign or session manual ad content. Email signups by pin = key event filtered the same way
Why day one | GA4 cannot attribute retroactively — pins published without UTMs are permanently invisible in attribution. Never edit a live pin URL later; re-pin with the correct link instead

## Tools & Budget
Tool Stack & Budget (automation-first)
Tool | Cost | What it does for you | When | Verdict
Pinterest Business account | Free | Analytics, Rich Pins, native scheduler (30 days ahead, 100 pins) | Week 1 | Required
Canva Pro | $13/mo | Master templates, brand kit, bulk create (CSV -> 50 pins at once), animation for video pins, AI image gen included | Week 2 | Yes - the automation backbone
AI agent (replaces Fiverr designer) | $0 incremental | Generates templates/cards from prompts with explicit asset values (fonts, hex, logo URL) + STOP-and-report rules. QUALITY GATE REQUIRED: every batch visually reviewed before deploy — 2 of first 3 outputs needed rework (wrong font, thin weight). Fiverr designer remains the fallback at Week 6 review if pin save-rate underperforms. | Week 2 | Yes per your outsource preference - OR skip and use Canva bulk-create yourself
Ideogram (AI imagery) | Free tier / $8/mo | Best for illustrated backgrounds; better text-space composition than Midjourney for pins | Week 2 | Optional - Canva AI may suffice
Tailwind | $25/mo | Interval re-pinning, communities (group-board successor), best-time scheduling, deeper analytics | Week 7+, only if volume sustains | Defer - native scheduler first
Pinterest Tag | Free | Site event tracking, audience insights, prerequisite for any future ad test | Week 4 | Yes
Pin inspector / Pin Stats | Free (built-in analytics) | Per-pin saves/clicks for week-6 and week-12 review gates | Week 6 | Use built-in first
TOTAL monthly run-rate | ~$15-25/mo | Canva Pro + optional Ideogram; designer cost removed while AI-agent route holds | - | At 50-60 pins/month = $1-2 per pin all-in

## Pin Batch 1
Pin Batch 1 — Week 3 (12 pins, schedule 2/day)
Workflow per pin: open template SVG -> replace placeholders with Title (split across the two title lines) -> export PNG 1000x1500 -> upload to Pinterest -> paste Title, Description, URL exactly -> assign Board -> schedule. Mark Status when queued.
# | Pin ID (utm_content) | Template | Board | Pin Title | Pin Description | Destination URL (paste exactly) | Status
1 | checklist-01 | 1 Checklist | NYC Safety Tips | NYC Safety Checklist: 7 Habits for First-Time Visitors | Practical NYC safety tips for tourists — subway habits, scam awareness, and smart night-walking rules from a street-tested New York City safety guide. Save this checklist for your trip. | https://www.travelsamericas.com/destination/nyc/nyc-safety-guide?utm_source=pinterest&utm_medium=organic&utm_campaign=safety&utm_content=checklist-01
2 | checklist-02 | 1 Checklist | NYC Subway + Getting Around | NYC Subway at Night: 5 Rules I Always Follow | Riding the NYC subway alone at night? These 5 subway safety rules — where to stand, which car to pick, late-night transfer tips — keep solo travelers confident. | https://www.travelsamericas.com/destination/nyc/subway-safety-guide?utm_source=pinterest&utm_medium=organic&utm_campaign=safety&utm_content=checklist-02
3 | checklist-03 | 1 Checklist | NYC Solo Female Travel | Solo Female Travel NYC: Pre-Trip Safety Setup | Traveling to New York alone? 5 things to set up before you land — location sharing, backup payments, and the safety apps worth having. From our NYC solo female travel guide. | https://www.travelsamericas.com/destination/nyc/nyc-female-solo-travel-guide?utm_source=pinterest&utm_medium=organic&utm_campaign=safety&utm_content=checklist-03
4 | checklist-04 | 1 Checklist | NYC Safety Tips | Is NYC Safe at Night? 5 Things to Know | Walking NYC at night as a tourist: which areas stay busy, when to switch to rideshare, and the after-dark rules locals actually use. Honest night-safety breakdown. | https://www.travelsamericas.com/destination/nyc/is-nyc-safe-at-night?utm_source=pinterest&utm_medium=organic&utm_campaign=safety&utm_content=checklist-04
5 | itinerary-01 | 4 Itinerary | NYC Itineraries | 3 Days in NYC Alone: An Itinerary That Works | A realistic 3-day NYC itinerary for solo travelers — Central Park to the Brooklyn Bridge, with solo-friendly food stops and budget notes. Free printable PDF included. | https://www.travelsamericas.com/destination/nyc/solo-itinerary?utm_source=pinterest&utm_medium=organic&utm_campaign=planning&utm_content=itinerary-01
6 | itinerary-02 | 4 Itinerary | NYC Solo Female Travel | Solo Trip to NYC: The First-Timer’s Plan | Planning a solo trip to New York City? Where to stay, how to ride the subway with confidence, daily budgets, and a 3-day plan — built for first-time solo travelers. | https://www.travelsamericas.com/destination/nyc/solo-trip-to-nyc?utm_source=pinterest&utm_medium=organic&utm_campaign=solo&utm_content=itinerary-02
7 | itinerary-03 | 4 Itinerary | NYC Itineraries | Your First 24 Hours in NYC, Solo | The arrival-day plan that prevents day-one burnout: transit from JFK, a 30-minute orientation loop, and the easiest first solo dinner in New York City. | https://www.travelsamericas.com/destination/nyc/solo-trip-to-nyc?utm_source=pinterest&utm_medium=organic&utm_campaign=solo&utm_content=itinerary-03
8 | listicle-01 | 2 Listicle | Where to Stay in NYC | 7 Safest Areas to Stay in NYC, Compared | Where to stay in NYC as a solo traveler: 7 neighborhoods compared for safety, late-night walkability, and subway access — with the hotel zones worth paying for. | https://www.travelsamericas.com/destination/nyc/best-areas-to-stay?utm_source=pinterest&utm_medium=organic&utm_campaign=insider&utm_content=listicle-01
9 | map-01 | 3 Map | NYC Safety Tips | NYC After Dark: Walk Here, Ride There | An honest NYC neighborhood safety map for visitors — where streets stay lively at night, where to stay alert, and where a rideshare beats walking. Block-by-block guide. | https://www.travelsamericas.com/destination/nyc/neighborhood-guide?utm_source=pinterest&utm_medium=organic&utm_campaign=insider&utm_content=map-01
10 | listicle-02 | 2 Listicle | Where to Stay in NYC | Where to Stay in NYC: First Solo Trip Edition | First solo trip to New York? Stay between 14th and 96th in Manhattan, within 5 minutes of a subway line — plus 3 rules for picking a safe hotel block. | https://www.travelsamericas.com/destination/nyc/best-areas-to-stay?utm_source=pinterest&utm_medium=organic&utm_campaign=insider&utm_content=listicle-02
11 | pdf-01 | 4 Itinerary | NYC Itineraries | Free PDF: 3-Day NYC Solo Itinerary | Grab the free printable NYC itinerary — day-by-day plan, packing list, and budget breakdown, sent instantly. Made for first-time solo travelers to New York City. | https://www.travelsamericas.com/destination/nyc/solo-itinerary?utm_source=pinterest&utm_medium=organic&utm_campaign=planning&utm_content=pdf-01
12 | pdf-02 | 5 Stat | Solo Travel Tips for Women | NYC Packing List + 3-Day Plan (Free PDF) | What to pack for New York plus a complete 3-day solo plan in one free PDF — walking-shoe rules, subway payment tips, and a realistic budget table. Sent instantly. | https://www.travelsamericas.com/destination/nyc/solo-itinerary?utm_source=pinterest&utm_medium=organic&utm_campaign=planning&utm_content=pdf-02